## Ark1
TASKS |  |  |  | SCHEDULE
START/FINISH: APRIL 20th - MAY 24th 2020 |  |  |  | W1 [20.apr - 26.apr] | [6 empty] | W2 [27.apr - 3.may] | [6 empty] | W3 [4.may - 10.may] | [6 empty] | W4 [11.may - 17.may] | [6 empty] | W5 [18.may - 24.may]
| START | END | TIME | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su
PLANNING |  |  | 7d
Functional Specification | 2020-04-20 | 2020-04-23 | 4d | W1 [20.apr - 26.apr] Mo: 20; W1 [20.apr - 26.apr] Tu: 21; W1 [20.apr - 26.apr] We: 22; W1 [20.apr - 26.apr] Th: 23; W1 [20.apr - 26.apr] Sa: Research, work overview and general planning
Gantt Chart | 2020-04-24 | 2020-04-26 | 3d | W1 [20.apr - 26.apr] Fr: 24; W1 [20.apr - 26.apr] Sa: 25; W1 [20.apr - 26.apr] Su: 26; W2 [27.apr - 3.may] Tu: Gannt creation and project planning
RESEARCH |  |  | 3d
Research | 2020-04-27 | 2020-04-27 | 1d | W2 [27.apr - 3.may] Mo: 27; W2 [27.apr - 3.may] We: Competitor research, user research
Target audience | 2020-04-28 | 2020-04-28 | 1d | W2 [27.apr - 3.may] Tu: 28; W2 [27.apr - 3.may] Th: Information Architecture etc
Creating personas, scenarios & storyboard | 2020-04-29 | 2020-04-29 | 1d | W2 [27.apr - 3.may] We: 29; W2 [27.apr - 3.may] Th: Create personas, scenarios and storyboard
WIREFRAME |  |  | 4d
Wireframe | 2020-04-30 | 2020-05-01 | 2d | W2 [27.apr - 3.may] Th: 30; W2 [27.apr - 3.may] Fr: 1; W2 [27.apr - 3.may] Sa: Create detailed wireframe/mindmap for the page structure
Prototyping | 2020-05-02 | 2020-05-03 | 2d | W2 [27.apr - 3.may] Sa: 2; W2 [27.apr - 3.may] Su: 3; W3 [4.may - 10.may] Tu: Create sketches and final prototyping in Adobe Xd
DESIGN |  |  | 3d
Research | 2020-05-04 | 2020-05-04 | 1d | W3 [4.may - 10.may] Mo: 4; W3 [4.may - 10.may] We: Browse similar pages
Layouts & Images | 2020-05-05 | 2020-05-05 | 1d | W3 [4.may - 10.may] Tu: 5; W3 [4.may - 10.may] Th: Gather images, convert images, layout considerations etc
Fonts & Colors | 2020-05-05 | 2020-05-05 | 1d | W3 [4.may - 10.may] Tu: 5; W3 [4.may - 10.may] Th: Choose fonts and make color palette, cta colors etc.
Navigation design | 2020-05-06 | 2020-05-06 | 1d | W3 [4.may - 10.may] We: 6; W3 [4.may - 10.may] Fr: Review and decisioning about general navigation on page
Interaction design | 2020-05-06 | 2020-05-06 | 1d | W3 [4.may - 10.may] We: 6; W3 [4.may - 10.may] Fr: UI (visual design, interface, branding, graphics etc.)
PROGRAMMING |  |  | 14d
Research & Content creaction | 2020-05-07 | 2020-05-08 | 1d | W3 [4.may - 10.may] Th: 7; W3 [4.may - 10.may] Fr: 8; W3 [4.may - 10.may] Su: Gather resources, articles, videos and images
Front page (HTML/CSS base) | 2020-05-09 | 2020-05-10 | 2d | W3 [4.may - 10.may] Sa: 9; W3 [4.may - 10.may] Su: 10; W4 [11.may - 17.may] Tu: HTML/CSS Programming
Image of the day (HTML/CSS base) | 2020-05-11 | 2020-05-12 | 2d | W4 [11.may - 17.may] Mo: 11; W4 [11.may - 17.may] Tu: 12; W4 [11.may - 17.may] Th: HTML/CSS Programming
Image/Video Gallery Page (HTML/CSS base) | 2020-05-13 | 2020-05-14 | 2d | W4 [11.may - 17.may] We: 13; W4 [11.may - 17.may] Th: 14; W4 [11.may - 17.may] Sa: HTML/CSS Programming
Article page (HTML/CSS base) | 2020-05-15 | 2020-05-16 | 2d | W4 [11.may - 17.may] Fr: 15; W4 [11.may - 17.may] Sa: 16; W5 [18.may - 24.may] Mo: HTML/CSS Programming
Choosing relevant API | 2020-05-17 | 2020-05-17 | 1d | W4 [11.may - 17.may] Su: 17; W5 [18.may - 24.may] Tu: API
JavaScript coding | 2020-05-18 | 2020-05-19 | 2d | W5 [18.may - 24.may] Mo: 18; W5 [18.may - 24.may] Tu: 19; W5 [18.may - 24.may] Th: JS
HTML review | 2020-05-20 | 2020-05-20 | 1d | W5 [18.may - 24.may] We: 20; W5 [18.may - 24.may] Fr: HTML rew
CSS review | 2020-05-20 | 2020-05-20 | 1d | W5 [18.may - 24.may] We: 20; W5 [18.may - 24.may] Fr: CSS rew
Media coding | 2020-05-21 | 2020-05-21 | 1d | W5 [18.may - 24.may] Th: 21; W5 [18.may - 24.may] Fr: @Media
IMPLEMENTATION |  |  | 3d
Bugfix | 2020-05-22 | 2020-05-22 | 1d | W5 [18.may - 24.may] Fr: 22
User testing | 2020-05-22 | 2020-05-22 | 1d | W5 [18.may - 24.may] Fr: 22
Rollout | 2020-05-22 | 2020-05-22 | 1d | W5 [18.may - 24.may] Fr: 22
Report | 2020-05-23 | 2020-05-24 | 2d | W5 [18.may - 24.may] Sa: 23; W5 [18.may - 24.may] Su: 24